## Sheet1
Indus Travels
http://industravels.net
SNO | Rquirement Code | Description | aspx page | Developer Name | Start Date | End Date | status (%) | Tester Name | Tester Start Date | Tester End Date | Test Status (%) | Tester Remarks | Show Stoppers
1 | RITH0000001 | Home Page Content has to be changed | http://industravels.net/Default.aspx | Vasanth | 16/9/2014 | 20/9/2014 | 100% | Mona
2 | RITH0000002 | Remove 'forums tab' from Home Page Main & cruises link to be updated | http://industravels.net/Default.aspx | Vasanth | 19/9/2014 |  | 50%
3 | RITH0000003 | homepage below the first line tabs , 'Register' advertisement has to be removed from the blue line | http://industravels.net/Default.aspx | Vasanth | 18/9/2014 | 18/9/2014 | 100%
4 | RITH0000004 | The images with the flash, shouldbe more clear and the whiteness between the change in image has to be removed. | http://industravels.net/Default.aspx | Sharada | 17/9/2014 | 19/9/2014 | 100%
5 | RITH0000005 | The scrolling of the words on the flash imagess has to be reduced and corrected. | http://industravels.net/Default.aspx | Sharada | 17/9/2014 | 19/9/2014 | 100%
6 | RITH0000006 | All images in homepage has be linked with respective package details with no costing. | http://industravels.net/Default.aspx |  | 20/9/2014 | 22/9/2014 | 100%
7 | RITH0000007 | Combine 'Travel Services' and 'Travel Other services options ' as 'Travel services | http://industravels.net/Default.aspx |  | 20/9/2014 | 20/9/2014 | 100%
8 | RITH0000008 | Homepage least bottom line , regarding the tabs has to be discussed. | http://industravels.net/Default.aspx
10 | RITC0000001 | Company Page Content has to be changed | http://industravels.net/Company.aspx | Vasanth | 18/9/2014 | 20/9/2014 | 100%
11 | RITC0000002 | Corrsponding pages to be linked to left hand and right hand sideimages of company page. | http://industravels.net/Company.aspx |  | 22/9/2014 | 22/9/2014 | 100%
12 | RITPS0000001 | Product & Services page Content has to be changed | http://industravels.net/Product.aspx
13 | RITHP0000001 | In Holiday packages page, Book button and NA option has to be removed | http://industravels.net/HolidaySpot.aspx | Ravi | 17/9/2014 | 17/9/2014 | 100% | [5 empty] | Removed
14 | RITV0000001 | In visa page, corresponding information (links) will be provided | http://industravels.net/VisitIndia.aspx | Arun,Vasanth
15 | RITG0000001 | selected menu item should be highlighted |  | Ravi | 22/9/2014 | 22/9/2014 | 100%
16 | RITH0000001 | Travel Insurance content has to prepared | http://industravels.net/Default.aspx#
17 | RITCR0000001 | Links has to be added to the cruises tab | http://industravels.net/Cruises.aspx
18 | RITSO000001 | Links and content has to be added up for Special offers Tab | http://industravels.net/Spcial.aspx | Ravi | 23/09/2014 |  | 50%
19 | RITI000001 | Insurance | http://industravels.net/Insurance.aspx | sarada | 23/09/2014
20 | ON HOLD | In home page, Regarding the services of Airlines , hotels, Buses, rail has to be discussed.
21
22
23
24
25
26
27
28
29
30
31
32